## Sheet1
Individual Responsible | Date | Task Name | Task Description | Time Spent | Running total
Keagan Foster | 13/08 | Solution setup | Recieved smart glasses and setup my solution at uni, as well as testing some Android Studio methods of video streaming | 2:00 | 2:00
| 14/08 | Testing solution on smart-glasses | Worked on implementing my solution onto smartglasses, achieved succes in finding a path to a working solution through using a Firefox apk which has more functionality than the default browser. | 5:00 | 7:00
| 15/08 | Getting server running & Web RTC for AS | Got online server working using git and heroku which works and before that was testing out using webrtc libaries for Android studio | 5:00 | 12:00
| 16/08 | Supervisor Meeting | Attended and particpated in supervisor meeting | 1:00 | 13:00
| 16/08 | Sharing and testing and improving code | Worked with Jimmy and Krishna to test and improve my code to make it run faster | 3:00 | 16:00
| 16/08 | Team meeting | Attended and particpated in team meeting | 1:00 | 17:00