## Week 1
Individual Responsible | Date | Task Name | Task Description | Time Spent | Running total
Shenal Nirushka | 26/08/2018 | installing open CV | Attempting to install opeCV and node js | 3 | 4
| 27/08/2018 | team meeting | Weekly team meeting | 2 | 6
| 27/08/2018 | installing open CV | installing and running open CV | 4 | 10

## Week 2
Overseas

## Week 3
Individual Responsible | Date | Task Name | Task Description | Time Spent | Running total
Jimmy Li | 12/03/2018, Monday | Meeting | Team Meeting | 2 | 2
| 12/03/2018, Monday | Research | Analysing project case | 1 | 3
| 12/03/2018, Monday | Research | Computer Vision | 2 | 5
| 13/03/2018, Tuesday | Research | Analyse project requirments | 2 | 7
| 15/03/2018, Thursday | Meeting | Supervisor Meeting | 1 | 8
| 15/03/2018, Thursday | Meeting | Informal Team Meeting | 1 | 9
| 15/03/2018, Thursday | Meeting | Client Meeting | 1 | 10
| 15/03/2018, Thursday | Research | Further Analyse client requirments from meeting | 2 | 12
| 13/03/2018, Tuesday | Research | Hardware specifications of Vuzix M100 Smartglass | 0.5 | 12.5
|  |  |  | Total | 12.5

## Week 4
Individual Responsible | Date | Task Name | Task Description | Time Spent | Running total
Jimmy | 19/03/2018, Monday | Research | Methods of team mangement and software requirments books | 2 | 2
| 19/03/2018, Monday | Team management and administration | Organise team members for the Software Requirements Specifics document | 1 | 3
| 19/03/2018, Monday | Team Documents Writing | Documenting the Software Requirements Specifics | 2 | 5
| 20/03/2018, Tuesday | Software | Setting up android IDE, attempt to create development environment | 2 | 7
| 22/03/2018, Thursday | Team and supervisor meetings | Supervisor Meeting | 1 | 8
| 22/03/2018, Thursday | Team and supervisor meetings | Informal Team meeting | 1.5 | 9.5
| 22/03/2018, Thursday | Client meetings | Client Meeting | 1 | 10.5
| 25/03/2018, Sunday | Team and supervisor meetings | Social event with team | 3.5 | 14
|  |  |  | Total | 14

## Week 5
Individual Responsible | Date | Task Name | Task Description | Time Spent | Running total
Jimmy | 26/03/2018, Monday | Team and supervisor meetings | Team meeting | 2 | 2
| 26/03/2018, Monday | Research | Android camera, android studio, android studio environment setup, how to implement object recognition into our system: python, opencv, tensorflow | 4 | 6
| 27/03/2018, Monday | Software | Setting up test environment for the project with opencv(jave flavour) on android studio, integrating opencv in to the IDE | 2 | 8
| 03/04/2018, Tuesday | Team Documents Writing | Worked on the use case diagram, created the initial diagram on Lucidchart | 1.5 | 9.5
| 03/04/2018, Tuesday | Research | Research on methods of video segmentation for hand gesture recognition using camera | 0.5 | 10
| 03/04/2018, Tuesday | Team and supervisor meetings | Team Meeting | 4 | 14
| 05/04/2018, Thursday | Team and supervisor meetings | Supervisor Meeting | 1 | 15
|  |  |  | Total | 15

## Week 6
Individual Responsible | Date | Task Name | Task Description | Time Spent | Running total
Jimmy | 09/04/2018, Monday | Research | Finding new tool for creating diagrams, due to usage limit on lucidchart. Switching to StarUML | 1 | 1
| 09/04/2018, Monday | Team Documents Writing | Updated the Software requirement specifics document | 4 | 5
| 09/04/2018, Monday | Team Documents Writing | Updated use case diagram | 1 | 6
| 09/04/2018, Monday | Team and supervisor meetings | Team Meeting | 2 | 8
| 10/04/2018, Tuesday | Team Documents Writing | Continue work on use case diagram | 2 | 10
| 10/04/2018, Tuesday | Research | Reseach on UML 2.0 rules and standards | 1 | 11
| 11/04/2018, Wednesday | Team Documents Writing | Begin work on activity diagrams | 2.5 | 13.5
| 11/04/2018, Wednesday | Research | Reseach on Activity Diagram standards | 1 | 14.5
| 11/04/2018, Wednesday | Team Documents Writing | Begin work on use case descriptions | 1 | 15.5
| 12/04/2018, Thursday | Research | Research on the android architecture, UML standards, and ways to facilitate cross devices communication on a wireless local network(WLAN) between android devices | 2 | 17.5
| 12/04/2018, Thursday | Other | Setting up team github | 0.5 | 18
| 13/04/2018, Friday | Team Documents Writing | Continue work on the SRS | 2 | 20
| 15/04/2018, Sunday | Team Documents Writing | Continue work on the SRS and use case diagrams | 3 | 23
|  |  |  | Total | 23

## Week 7
Individual Responsible | Date | Task Name | Task Description | Time Spent | Running total
Jimmy | 16/04/2018, Monday | Team and supervisor meetings | Supervisor Meeting | 1 | 1
| 17/04/2018, Tuesday | Team Documents Writing | Continue work on the SRS, added more use case descriptions | 1 | 2
| 19/04/2018, Thursday | Team and supervisor meetings | Team Meeting | 1 | 3
| 19/04/2018, Thursday | Client meetings | Client Meeting | 1.5 | 4.5
| 20/04/2018, Friday | Software | SPIKE: programming the video communication feature | 5 | 9.5
|  |  |  | Total | 9.5

## Week 8
Individual Responsible | Date | Task Name | Task Description | Time Spent | Running total
Jimmy | 23/04/2018, Monday | Team and supervisor meetings | Supervisor Meeting | 1 | 1
| 23/04/2018, Monday | Team management and administration | Team manageent, delegate tasks | 1 | 2
| 24/04/2018, Tuesday | Team Documents Writing | WBS - Updated and uploaded | 3 | 5
| 25/04/2018, Wednesday | Team Documents Writing | SRS - Updated and emailed to Jun | 4 | 9
| 26/04/2018, Thursday | Software | Video streaming in Android studio with the glasses | 3 | 12
| 26/04/2018, Thursday | Team and supervisor meetings | Team meeting | 1.5 | 13.5
| 29/04/2018, Sunday | Team and supervisor meetings | Skype meeting with Lyndon | 1 | 14.5
| 29/04/2018, Sunday | Research | Research suitable streaming API capable with Andorid 4.0.4 | 1 | 15.5
| 29/04/2018, Sunday | Software | Programming camera with MediaRecorder API on Android 4.0.4 | 2 | 17.5
|  |  |  | Total | 17.5

## Week 9
Individual Responsible | Date | Task Name | Task Description | Time Spent | Running total
| 02/05/2018, Wednesday | Team Documents Writing | SRS - added versioning, updated user interfaces and wireframes | 3 | 3
| 02/05/2018, Wednesday | Software | Getting video streaming to work on the device, sucessfully implemented video preview. Video streaming to server remained unsuccessful | 5 | 8
| 03/05/2018, Thursday | Team and supervisor meetings | Team Meeting | 2 | 10
| 03/05/2018, Thursday | Team Documents Writing | Class Diagram | 2 | 12
| 03/05/2018, Thursday | Team management and administration | Allocating tasks to memebers | 1 | 13
| 05/05/2018, Saturday | Research | Alternative/simpler method of capturing and streaming videos cross the network | 3 | 16
| 06/05/2018, Sunday | Team Documents Writing | Update individual research plan | 2 | 18
| 06/05/2018, Sunday | Research | Update prototype on marvel | 1 | 19
|  |  |  | Total | 19

## Week 10
Individual Responsible | Date | Task Name | Task Description | Time Spent | Running total
| 07/05/2018, Monday | Team and supervisor meetings | Supervisor Meeting | 1 | 1
| 07/05/2018, Monday | Research | Research Report | 1.5 | 2.5
| 07/05/2018, Monday | Team and supervisor meetings | Team meeting @230pm | 2 | 4.5
| 07/05/2018, Monday | Software Development | Prototype | 1 | 5.5
| 08/05/2018, Tuesday | Software Development | Prototype | 3 | 8.5
| 08/05/2018, Tuesday | Team Documents Writing | SRS V1.2 Update, added more details regarding to the object measuring function, performance requirements and feature tree | 0.5 | 9
| 09/05/2018, Wednesday | Software Development | Prototype | 2 | 11
| 10/05/2018, Thursday | Client meetings | Client Meeting | 1 | 12
| 10/05/2018, Thursday | Team and supervisor meetings | Team meeting | 0.5 | 12.5
| 11/05/2018, Friday | Team Documents Writing | SRS v1.3 update | 6 | 18.5
| 13/05/2018, Sunday | Research | Research Report | 2 | 20.5
|  |  |  | Total | 20.5

## Week 11
Individual Responsible | Date | Task Name | Task Description | Time Spent | Running total
| 14/05/2018, Monday | Team and supervisor meetings | Supervisor Meeting | 1 | 1
| 15/05/2018, Tuesday | Presentations Preparing | Get green screen. Presentation planning. | 3 | 4
| 16/05/2018, Wednesday | Presentations Preparing | Video recording and presentation planning | 4 | 8
| 17/05/2018, Thursday | Presentations Preparing | Video and audio recording for presentation | 4 | 12
| 17/05/2018, Thursday | Team and supervisor meetings | Team meeting | 2 | 14
| 18/05/2018, Friday | Presentations Preparing | Presentaiton credits | 2 | 16
| 19/05/2018, Sunday | Software | Software architecture | 2.5 | 18.5
|  |  |  | Total | 18.5

## Week 12
Individual Responsible | Date | Task Name | Task Description | Time Spent | Running total
| 21/05/2018, Monday | Team and supervisor meetings | Supervisor Meeting | 1 | 1
| 23/05/2018, Wednesday | Software Development | Software architecture diagrams: package diagram, deployment diagram, component diagram, CRC cards | 7 | 8
| 24/05/2018, Thursday | Team Documents | Self Assessment document | 4 | 12
| 24/05/2018, Thursday | Team and supervisor meetings | Team meeting | 2.5 | 14.5
|  |  |  | Total | 14.5