## Sheet1
Individual Responsible | Date | Task Name | Task Description | Time Spent | Running total
Keagan Foster | 16/04 | Team Meeting | Before supervisor meeting small informal team meeting occured | 0:30 | 0:30
| 16/04 | Supervisor Meeting | Meet with and discussed team progress with supervisor | 1:00 | 1:30
| 16/04 | Team Discussion | After supervisor meeting, team discussion in classroom occured were issues were resolved | 0:30 | 2:00
| 16/04 | Lecture | Watched unit lecture online | 2:00 | 4:00
| 18/04 | Project Plan | Updated Project plan to better represent plan for team, with new information gained in supervisor meeting | 2:00 | 6:00
| 20/04 | Team Meeting | Formal team meeting and work session | 2:00 | 8:00
| 20/04 | Team Management | Organising and aiding subteam and whole team with direction they need to work towards | 0:30 | 8:30
| 20/04 | Pre-Client team meeting | Before client meeting, management discussed required items for client meeting | 0:30 | 9:00
| 20/04 | Client Meeting | Client meeting discussing progress and planning | 1:00 | 10:00
| 20/04 | Post-Client management meeting | After client meeting, we talked about archictecture planning | 0:30 | 10:30
| 21/04 | Software Research | Research required software and downloading Android CV | 1:00 | 11:30