## Sheet1
Individual Responsible | Date | Task Name | Task Description | Time Spent | Running total
Jimmy | 23/04/2018, Monday | Team and supervisor meetings | Supervisor Meeting | 1 | 1
| 23/04/2018, Monday | Team management and administration | Team manageent, delegate tasks | 1 | 2
| 24/04/2018, Tuesday | Team Documents Writing | WBS - Updated and uploaded | 3 | 5
| 25/04/2018, Wednesday | Team Documents Writing | SRS - Updated and emailed to Jun | 4 | 9
| 26/04/2018, Thursday | Software | Video streaming in Android studio with the glasses | 3 | 12
| 26/04/2018, Thursday | Team and supervisor meetings | Team meeting | 1.5 | 13.5
| 29/04/2018, Sunday | Team and supervisor meetings | Skype meeting with Lyndon | 1 | 14.5
| 29/04/2018, Sunday | Research | Research suitable streaming API capable with Andorid 4.0.4 | 1 | 15.5
| 29/04/2018, Sunday | Software | Programming camera with MediaRecorder API on Android 4.0.4 | 2 | 17.5
|  |  |  | Total | 17.5