## Sheet1
Individual Responsible | Date | Task Name | Task Description | Time Spent | Running total
Lyndon Prado
| 2018-05-06 | research report (3) and checking test plan (2) |  | 5 | 5
| 2018-05-07 | supervisor meeting |  | 1 | 6
| 2018-05-07 | quality assurance meeting |  | 2 | 8
| 2018-05-08 | assessment criteria(1.5), research report(1.5), presentation plan(1) |  | 4 | 12
| 2018-05-09 | criteria(.5), software architecture(.5), research report(1), team organisation(1), presentation(.5) |  | 3.5 | 15.5
| 2018-05-09 | review documentation - project plan(1),sqap(1),srs(.5),test plan(1) |  | 3.5 | 19
| 2018-05-10 | team meeting |  | 2 | 21
| 2018-05-10 | client meeting |  | 1 | 22
| 2018-05-11 | research paper |  | 5.5 | 27.5
| 2018-05-12 | research paper |  | 4 | 31.5
|  | team and supervisor meetings |  | 5 | 5
|  | client meetings |  | 1 | 6
|  | team management and administration |  | 2 | 8
|  | research |  | 3 | 11
|  | software |  | 0 | 11
|  | presentations |  | 1.5 | 12.5
|  | team documents |  | 14.5 | 27
|  | reviewing |  | 7.5 | 34.5
|  | others |  |  | 34.5